## Sheet1
Tittle | Hours | Per/Hour | Total Cost | Status
Create Requirement Document | 4 | 10 | 40 | Completed
Create UML Diagrams | 3 | 11 | 33 | Completed
Create Text File for Feeding Database | 2 | 10 | 20
Create Database | 2 | 20 | 40
Open Connection/Create Database in Project | 5 | 20 | 100
Populate List with Data | 2 | 11 | 22
Sort List | 1 | 17 | 17
Poll Database Periodically | 2 | 17 | 34
Populate Map with Data | 3 | 17 | 51
Determine Threat Level of Sensor | 4 | 20 | 80
Select Subset of Sensors for Viewing | 3 | 14 | 42
Contact Authorities from Program | 2 | 12 | 24
Write JUnit Tests | 6 | 16 | 96
| 39 |  | 599